Logical Framework Matrix Comparison

The Logical Framework Matrix (LogFrame) is a systematic planning tool used extensively in project management, particularly within the development sector. This resource provides a comparative overview of terminologies and frameworks used by various organisations such as CARE, USAID, DANIDA, DfID, CIDA, GTZ, the European Union, FAO, UNDP, NORAD, UNHCR, the World Bank, and AusAID. By aligning project goals, objectives, outcomes, outputs, activities, and inputs, the LogFrame helps structure projects to ensure clarity, accountability, and measurable progress. This comprehensive resource breaks down the different terminologies and approaches these organisations use, clearly understanding how to effectively plan, implement, and evaluate projects. This comparison aids in fostering a unified approach to project management, facilitating better coordination, and enhancing the overall impact of development initiatives.

| Ultimate Impact | End Outcomes | Intermediate Outcomes | Outputs | Interventions |
| --- | --- | --- | --- | --- |
| Higher Consequence | Specific Problem | Cause | Solution | Process/Inputs |
| CARE terminology | Program Impact | Project Impact | Effects | Outputs |
| CARE log frame | Program Goal | Project Final Goal | Intermediate Objectives | Outputs |
| PC/LogFrame | Goal | Purpose | Outputs | Activities |
| USAID Results Framework | Strategic Objective | Intermediate Results | Outputs | Activities |
| USAID Logframe | Final Goal | Strategic Goal/Objective | Intermediate Results | Activities |
| DANIDA + DfID | Goal | Purpose | Outputs | Activities |
| CIDA + GTZ | Overall Goal | Project Purpose | Results/Outputs | Activities |
| European Union | Overall Objective | Project Purpose | Results | Activities |
| FAO + UNDP + NORAD | Development Objective | Immediate Objectives | Outputs | Activities |
| UNHCR | Sector Objective | Goal | Project Objective | Outputs |
| World Bank | Long-term Objectives | Short-term Objectives | Outputs | Activities |
| AusAID | Scheme Goal | Major Development Objectives | Outputs | Activities |

Ultimate Impact (Higher Consequence)

Definition: The broad, long-term change or benefit the project aims to achieve. Often aligned with larger organisational or societal objectives.

Example: Improve public health and reduce poverty levels.

End Outcomes (Specific Problem)

Definition: The specific problem that the project seeks to address, leading to the desired ultimate impact.

Example: Reduce the incidence of waterborne diseases in rural areas.

Intermediate Outcomes (Cause)

Definition: The intermediate changes or results that directly result from the project's activities and outputs, addressing the cause of the problem.

Example: Increase access to clean drinking water through infrastructure improvements.

Outputs (Solution)

Definition: The direct products or services the project delivers, representing the solutions to the specific problem.

Example: Construction of new wells and water purification systems.

Interventions (Process/Inputs)

Definition: The specific activities, processes, and inputs required to produce the outputs and achieve the outcomes.

Example: Training local workers, procuring materials, and constructing wells.

Comparison of Terminologies Across Organizations

- CARE Terminology:

- Program Impact: The long-term change resulting from the program.

- Project Impact: The specific impact of the project within the program.

- Effects: The changes resulting from the project's outputs.

- Outputs: The tangible products or services delivered.

- Activities: The tasks undertaken to produce outputs.

- Inputs: The resources required for activities.

- CARE Logframe:

- Program Goal: The overarching aim of the program.

- Project Final Goal: The ultimate goal of the project.

- Intermediate Objectives: The specific objectives bridge the outputs and final goal.

- Outputs: The immediate results of project activities.

- Activities: The actions taken to achieve outputs.

- Inputs: The resources required for activities.

- PC/LogFrame:

- Goal: The ultimate aim of the project.

- Purpose: The specific objective to be achieved.

- Outputs: The direct results of activities.

- Activities: The tasks undertaken to produce outputs.

- USAID Results Framework:

- Strategic Objective: The long-term objective aligned with the program.

- Intermediate Results: The intermediate changes leading to the strategic objective.

- Outputs: The immediate results of activities.

- Activities: The actions taken to achieve outputs.

- Inputs: The resources required for activities.

- USAID Logframe:

- Final Goal: The ultimate aim of the project.

- Strategic Goal/Objective: The intermediate goal leading to the final goal.

- Intermediate Results: The specific results contributing to the strategic goal.

- Activities: The tasks undertaken to achieve intermediate results.

- 202E: Specific inputs or resources required.

- DANIDA + DfID:

- Goal: The ultimate aim of the project.

- Purpose: The specific objective to be achieved.

- Outputs: The direct results of activities.

- Activities: The tasks undertaken to produce outputs.

- CIDA + GTZ:

- Overall Goal: The overarching aim of the project.

- Project Purpose: The specific objective to be achieved.

- Results/Outputs: The immediate results of activities.

- Activities: The tasks undertaken to achieve outputs.

- Inputs: The resources required for activities.

- European Union:

- Overall Objective: The broad aim of the project.

- Project Purpose: The specific objective to be achieved.

- Results: The immediate results of activities.

- Activities: The tasks undertaken to achieve outputs.

- FAO + UNDP + NORAD:

- Development Objective: The long-term objective of the project.

- Immediate Objectives: The specific changes or results to be achieved.

- Outputs: The direct results of activities.

- Activities: The tasks undertaken to produce outputs.

- Inputs: The resources required for activities.

- UNHCR:

- Sector Objective: The overarching aim within a specific sector.

- Goal: The ultimate aim of the project.

- Project Objective: The specific objective to be achieved.

- Outputs: The direct results of activities.

- Activities: The tasks undertaken to produce outputs.

- Input/Resources: The resources required for activities.

- World Bank:

- Long-term Objectives: The broad, long-term aims of the project.

- Short-term Objectives: The specific, immediate aims to be achieved.

- Outputs: The direct results of activities.

- Activities: The tasks undertaken to produce outputs.

- Inputs: The resources required for activities.

- AusAID:

- Scheme Goal: The overarching aim of the project.

- Major Development Objectives: The specific, significant objectives to be achieved.

- Outputs: The direct results of activities.

- Activities: The tasks undertaken to produce outputs.